## Project Plan Template
Microclimate Station Network
| PROJECT TITLE |  | START DATE
| Microclimate Station Network |  | 2024-03-18 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  |  | in days
|  |  | 2024-12-01 |  |  | 259
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | Ý TƯỞNG VÀ KHỞI CÔNG DỰ ÁN | In Progress |  | 2024-03-18 | 2024-04-10 | 24 |  | Not Started
1.1 | Xác định ý tưởng | Complete |  | 2024-03-18 | 2024-03-18 | 1 |  | In Progress
1.2 | Đề xuất nội dung đề tài | In Progress |  | 2024-03-19 | 2024-03-27 | 9 |  | Complete
1.3 | Xác định các mục tiêu (Yếu tố môi trường) | Not Started |  | 2024-03-28 | 2024-03-28 | 1 |  | On Hold
1.4 | Xác định linh kiện, lên ngân sách | Not Started |  | 2024-03-29 | 2024-04-10 | 13
2 | QUY HOẠCH | Not Started |  | 2024-04-11 | 2024-05-05 | 25
2.1 | Xác định phần mềm sử dụng | Not Started |  | 2024-04-11 | 2024-04-12 | 2
2.2 | Test các thiết bị (cảm biến và các module) | Not Started |  | 2024-04-13 | 2024-04-27 | 15
2.3 | Test nguồn cấp ( Nguồn điện duy trì được bao lâu ?) | Not Started |  | 2024-04-28 | 2024-05-05 | 8
2.4 | Lên bản khảo cho sơ đồ nguyên lý (Gateway và Node) | Not Started |  | 2024-05-05 | 2024-05-19 | 15
3 | KHỞI CÔNG | Not Started |  | 2024-05-20 | 2024-10-30 | 164
3.1 | Vẽ PCB (GateWay và Node) | Not Started |  | 2024-05-20 | 2024-06-10 | 22
3.2 | Xây dụng mạng Lưới(LoraMesh) | Not Started |  | 2024-06-11 | 2024-07-11 | 31
3.3 | Kết hợp các module và cảm biến (dạng cấm dây) thực hiện truyền nhận | Not Started |  | 2024-07-12 | 2024-08-12 | 32
3.4 | Giao tiếp với phần mềm (Dạng cấm dây) | Not Started |  | 2024-08-12 | 2024-09-12 | 32
3.5 | Hoàn thành bản thử nghiệm (trên board vẽ từ pcb) | Not Started |  | 2024-09-13 | 2024-09-30 | 18
3.6 | Kiểm thử và hoàn hành | Not Started |  | 2024-10-01 | 2024-10-30 | 30
4 | THỰC HIỆN/ GIÁM SÁT | Not Started |  | 2024-11-01 | 2024-11-30 | 30
4.1 | Lắp đặt | Not Started |  | 2024-11-01 | 2024-11-07 | 7
4.2 | Giám sát và Đánh giá | Not Started |  | 2024-11-08 | 2024-11-30 | 23